## Sheet1
Project | Update | Start Date | End Date | Developer | Notes | Hand-Over Date | Feedback Date | Time-Lag(Days) | Status | Remarks
ATM Management Solution | Moved to configuration team for testing and UAT | 2016-08-08 | 2016-09-02 | Ayodeji Alabi |  | 2016-11-21 |  |  | Ongoing
Credit Crad Integration with EMP | Moved to configuration team for testing and UAT | 2016-10-03 | 2016-12-19 | Ayodeji Alabi |  | 2016-12-19 |  |  | Ongoing
POS Management Solution | Moved to configuration team for testing and UAT | 2016-10-04 | 2016-11-04 | Ayodeji Alabi |  | 2016-11-04 |  |  | Ongoing
In Branch POS | Pilot Launch Ongoing | 2016-09-28 | 2016-12-06 | Ayodeji Alabi |  | 2016-12-06 |  |  | Pilot
Modification of card Limit | Pending Update from interswitch on automating postillion resync | 2016-12-29 | 2017-01-19 | Ayodeji Alabi |  |  |  |  | Ongoing
BOTF | Moved to configuration team for testing and UAT | 2015-12-01 | 2016-10-15 | Adebowale Owoseni |  | 2016-11-15 |  |  | Ongoing
Legal Search | Integration Testing | 2017-01-09 | 2017-01-20 | Adebowale Owoseni |  | N/A |  |  | Ongoing
iCad NIBSS Integration | Moved to configuration team for testing and UAT | 2017-01-16 | 2017-02-12 | Adebowale Owoseni |  | 2017-02-08 |  |  | Ongoing
CallOver Portal Improvements | Moved to configuration team for testing and UAT | 2016-12-05 | 2016-12-30 | Adebowale Owoseni |  | 2017-01-03 |  |  | Ongoing
UnionAir | Review and Redesign of System Architecture | 2017-01-04 | N/A | Adebowale Owoseni |  | N/A |  |  | OnHold
Settlement Automation | Development in progress | 2016-10-11 | 2017-03-30 | Tolulope Bewaji |  |  |  |  | Ongoing
Customer Engagement Portal | Moved to configuration team for testing and UAT | 2016-11-04 | 2016-12-28 | Tolulope Bewaji |  | 2016-12-28
Union Acquirer Enhancement | CCB Approved to Deploy | 2016-07-12 | 2016-11-21 | Tunde Yakubu | CCB Approved, To be deployed to Live. | 2016-11-16 | 2016-11-21 |  | To Be Deployed To Live
CR: MODIFICATION OF ROLE RIGHTS ON LOAN SCORING MODULE | Development completed -Testing | 2016-12-28 | 2017-01-03 | Tunde Yakubu | Testing | 2017-01-03 |  |  | Testing
MODIFICATION TO RTGS PLATFORM ON OMNIFLOW | Development completed -Testing | 2017-01-05 | 2017-01-31 | Tunde Yakubu | Testing | 2017-01-09 |  |  | Testing
Retail Re-Segmentation for Account Opening (OmniFLow) | Development completed -Testing | 2017-01-05 | 2017-01-31 | Tunde Yakubu | Testing | 2017-01-10 |  |  | Testing
Change Request - To Include A Request Type (FX Purchase) on Omniflow. | Development completed -Testing | 2016-11-11 | 2016-12-08 | Tunde Yakubu | Testing | 2016-12-08 |  |  | Testing
Enhancements to Account Maintenance Form on Omniflow | Development completed -Testing | 2017-01-05 | 2017-01-31 | Tunde Yakubu | Testing | 2017-02-03 | 2017-02-06 |  | Testing
Oyo State Integration on Union Collect | CCB Approved to Deploy | 2017-02-06 | 2017-02-08 | Tunde Yakubu | Deployed To live | 2017-02-06 | 2017-02-08 |  | Deployed To live
Self Employed - Loan Scoring Platform | Development | 2017-02-06 |  | Tunde Yakubu | Development |  |  |  | Development
Card Management System | Development | 2016-12-28 | 2017-03-31 | Augustine Okore | Theresa Ereme still to provide written documentation on the implementation of card segmentation and all other requirements not captured on the BRS. | 2016-10-07 | 2017-03-31 |  | Ongoing
USSD Merchant Payment | LIVE and Pilot Test | 2016-11-07 | 2017-01-31 | Augustine Okore |  | 2017-02-08 |  |  | Pilot Testing Stage
RIA Money | Development | 2016-12-19 | 2017-01-21 | Okechukwu Okafor/Babatunde Adedeji | Development Completed and moved to Configuration and Testing Team | 2017-01-21 |  |  | Testing
Unclaimed MCs | Testing | 2017-01-09 | 2017-01-27 | Babatunde Adedeji | Testing ongoing | 2017-01-30 |  |  | Testing
Issuance of Debit Card on Domiciliary Account | Integration Testing | 2017-02-06 | 2017-02-10 | Babatunde Adedeji | System Integration Testing |  |  |  | Ongoing
Automation of Saving Withdrawal booklet charges | Moved to the Project Manger, The branch code from AD is not updated and the application relys on branch code from AD | 2017-01-12 | 2017-02-10 | Samuel Ezeala | The Project manager is to liase with HR and internal control so as to update bank branch codes on AD | 2017-02-06 | 2017-03-03
Internet Banking | Rounding up phase 1 | 2016-05-01 | 2017-03-15 | Toluwase Ashaolu | Development ongoing |  |  |  | Ongoing
Account Enquiry Portal | Moved to configuration team for testing and UAT | 2017-01-24 | 2017-02-03 | Dasylva Ayodeji | Moved to configuration team for testing and UAT | 2017-02-08 |  |  | Ongoing
Account Management Portal | Development | 2017-01-30 | 2017-02-24 | Dasylva Ayodeji | Development ongoing |  |  |  | Ongoing
Union Online Shopping Mall | Returned from Config and Testing unit for Correction | 2017-02-09 | 2017-03-03 | Samuel Ezeala | There was a flaw with the process flow captured in the BRS. At the point of payment the customer have to input their account number, which makes the system porous as user can iput a different account number not tire to him/her | 2017-03-03 | 2017-03-14 |  | Modification Ongoing
Modification of Bank of the Future Application | Moved to configuration team for testing and UAT | 2017-03-06 | 2017-03-10 | Samuel Ezeala | Moved to configuration team for testing and UAT | 2017-03-10 |  |  | Testing
Customer RM Change Notification | Development | 2017-03-13 | 2017-03-17 | Malik/Samuel